## Slide 2: What is an Urban Forest Master Plan?
20-year planning document identifying a vision, goals, and guiding principles for managing the city’s urban forest. It will use an adaptive management approach with 5-year implementation cycles including key steps and priorities with performance indicators for tracking progress.

## Slide 3
PHASE 1 – what do we have?
what do we want?
PHASE 2 – how do we get there?

## Slide 4: Process Schedule
Project | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan 25’ | Feb
Public Outreach: public meetings, tabling events, surveys, Engage Fairfax |  |  |  |  |  |  |  |  | 
Stakeholder Participation: steering committee, stakeholder interviews |  |  |  |  |  |  |  |  | 
State of the Urban Forest: policy review, invasive assessment, program/resource evaluation |  |  |  |  |  |  |  |  | 
Master Plan: draft outline |  |  |  |  |  |  |  |  | 
Phase 1
stakeholder interviews
development
Public meeting
Tabling events
Steering committee
review
summarize
JULY 25

## Slide 5: Process Schedule
Project | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
Public Outreach: public meetings, tabling events, survey, Engage Fairfax |  |  |  |  |  |  |  |  | 
Stakeholder Participation: steering committee |  |  |  |  |  |  |  |  | 
Master Plan: transition outline to 1st draft |  |  |  |  |  |  |  |  | 
Master Plan: Final draft and adoption |  |  |  |  |  |  |  |  | 
Phase 2
stakeholder follows as needed
development
Public meeting
Tabling events
Steering committee
development
Public hearings

## Slide 6: Project Components
Engagement Plan – active document for public engagement guided by the Steering Committee
Steering Committee – 12 members (Planning, Sustainability, Parks, Public Works, ESC)
Invasive Species Assessment & Action Plan – all city parks, trails, and wooded city parcels
Urban Forest Master Plan – final document
5-Year Implementation Plan & Activation – first set of key steps, resource needs, and program priorities

## Slide 7: ESC’s Role and Opportunities
Steering Committee – Ben and Rusty
Project Tabling – Arbor Day 2024
Stakeholder interview – late Fall/winter 2025
Adoption – support

## Slide 8
Engage Page Open
Invasive Species Survey
Closes 6/30/2024
July 25 Open House
Sherwood Center 6-8 pm